## D-Shell en kernels
D-Hydro team (BOOT) |  |  | Planning 31 march
|  |  | S = 0.5 sprint, M= 1 sprint, L = 1.5 sprints, XL = 2 sprints, XXL = 3 sprints |  |  |  | Release Kernels
sprint | week | first day | Sprint goals (prioritized every Friday) | teamfocus | Goals Kernels | Release D-Shell comp | Kernels | Events | Student testers
Sprint 1 | week 5 | 2017-01-30 | 2D-Morphology (L) | 0.5 | ?issuenr?: Delft3D Linux distribution
| week 6 | 2017-02-06 |  |  | ?issuenr?: FM 2D-Morphology
Sprint 2 | week 7 | 2017-02-13 | 2D-Morphology (L) | 0.5 | ?issuenr?: FM 2D-Wave
| week 8 | 2017-02-20 |  |  | ?issuenr?: DIMR: time issues | Patch release D-Hydro 1.2.4 / SOBEK 3.6.4 |  |  | x
Sprint 3 | week 9 | 2017-02-27 | 2D-Morphology (L) | 0.7 | ?issuenr?: RTC-Tools 1.x: no optimization
| week 10 | 2017-03-06 |  |  | ?issuenr?: Testbenches (DIMR, FM)
Sprint 4 | week 11 | 2017-03-13 | B&O sprint, Versnelling DS voor grote modellen | 0.7 | ?issuenr?: merge D3D-WAVE with D-WAVE
| week 12 | 2017-03-20 |  |  |  | Patch release D-Hydro 1.2.5 / SOBEK 3.6.5 | Feature freeze kernels 1.2.7 |  | x
Sprint 5 | week 13 | 2017-03-27 | Finishing 2D-Morphology (L) | 0.7 |  |  | Feature freeze DIMR
| week 14 | 2017-04-03 |  |  |  |  | Delivery to Delta Shell | FM Courses and D-Waq courses
Sprint 6 | week 15 | 2017-04-10 | Finishing 2D-Morphology (L) | 0.7
| week 16 | 2017-04-17 |  |  |  | Patch release D-Hydro 1.2.7 / SOBEK 3.6.7 |  |  | x
Sprint 7 | week 17 | 2017-04-24 | 1D-2D Flooding Polder (M) | 0.6 |  |  | Feature freeze kernels 1.2.8
| week 18 | 2017-05-01 |  |  |  |  | Feature freeze DIMR
Sprint 8 | week 19 | 2017-05-08 | 1D-2D Flooding Polder (M) | 0.6 |  |  | Delivery to Delta Shell
| week 20 | 2017-05-15 | [6 empty] | x
Sprint 9 | week 21 | 2017-05-22 | 2D Flooding Extra Polder, GUI edit links breach grow scripts | 0.8 |  | Do 25 mei: Rehearsal release D-Hydro 1.3.0 / SOBEK 3.7.0 | Feature freeze kernels 1.2.9 | Opleveren 1D2D polder Flooding aan BfG | x
| week 22 | 2017-05-29 |  |  |  |  | Feature freeze DIMR
| week 23 | 2017-06-05 | 2D Flooding Extra Polder, Release bugs | 0.8 |  |  | Delivery to Delta Shell
Sprint 10 | week 24 | 2017-06-12 |  |  |  |  | Feature freeze kernels 1.2.10 | DSD-NL | x
| week 25 | 2017-06-19 | 2D Flooding Extra Polder, Release bugs, GUI edit links breach grow scripts | 1 |  | Do 22 juni: Release 2017.1 D-Hydro 1.3.1 / SOBEK 3.7.1 | Feature freeze DIMR |  | x
| week 26 | 2017-06-26 |  |  |  |  | Delivery to Delta Shell
Sprint 11 | week 27 | 2017-07-03 | D-FlowFM: 6e generation-> editor voor General structure (M), Visualisatie Grid snapped features (S), Observationpoints en mappenstructuur | 1
| week 28 | 2017-07-10 |  |  |  | Patch release NGHS D-Hydro 1.3.2 / SOBEK 3.7.2 | Feature freeze kernels 1.2.11 |  | x
| week 29 | 2017-07-17 | D-FlowFM: 6e generation-> editor voor General structure (M), Visualisatie Grid snapped features (S), Observationpoints en mappenstructuur | 1 |  |  | Feature freeze DIMR
Sprint 12 | week 30 | 2017-07-24 |  |  |  |  | Delivery to Delta Shell
| week 31 | 2017-07-31 | Persistency (XXL) | 1
| week 32 | 2017-08-07 |  |  |  | Patch release D-Hydro 1.3.3 / SOBEK 3.7.3 | Feature freeze kernels 1.2.12 |  | x
Sprint 13 | week 33 | 2017-08-14 | Persistency (XXL) | 1 |  |  | Feature freeze DIMR
| week 34 | 2017-08-21 |  |  |  |  | Delivery to Delta Shell
| week 35 | 2017-08-28 | Persistency (XXL) | 1
Sprint 14 | week 36 | 2017-09-04 |  |  |  | Patch release D-Hydro 1.3.4 / SOBEK 3.7.4 |  |  | x
| week 37 | 2017-09-11 | Urban & 1D (XL) | 1 |  |  | Feature freeze kernels 1.2.13
| week 38 | 2017-09-18 |  |  |  |  | Feature freeze DIMR
Sprint 15 | week 39 | 2017-09-25 | Urban & 1D (XL) | 1 |  |  | Delivery to Delta Shell
| week 40 | 2017-10-02 | [6 empty] | x
| week 41 | 2017-10-09 | Missing Sobek 2 functionalititeit, LSM regionaal (M) | 1 |  | Do 12 okt: Rehearsal release D-Hydro 1.3.5 / SOBEK 3.7.5 | Feature freeze kernels 1.2.14 |  | x
Sprint 16 | week 42 | 2017-10-16 |  |  |  |  | Feature freeze DIMR
| week 43 | 2017-10-23 | Pilot sprint RGFGrid-DS integration (M) | 0.8 |  |  | Delivery to Delta Shell | DSD-INT
| week 44 | 2017-10-30 | [5 empty] | DSD-INT | x
Sprint 17 | week 45 | 2017-11-06 | Online model inspection, finishing (L) | 1 |  | Do 9 nov: Release 2017.2 D-Hydro 1.3.6 / SOBEK 3.7.6 |  |  | x
| week 46 | 2017-11-13 |  |  |  |  | Feature freeze kernels 1.2.15
| week 47 | 2017-11-20 | Usability GUI/UX (L) | 1 |  |  | Feature freeze DIMR
Sprint 18 | week 48 | 2017-11-27 |  |  |  |  | Delivery to Delta Shell
| week 49 | 2017-12-04 |  | 1 |  |  |  |  | x
| week 50 | 2017-12-11 |  |  |  | Patch release D-Hydro 1.3.7 / SOBEK 3.7.7
Niet opgenomen in de planning |  |  | Usability GUI/UX (L)
Online model inspection, finishing (L)
Improve scripting (L)
3D visualisatie

## Kernels
D-Hydro team (BOOT) |  |  | Planning 2 februari
|  |  | S = 0.5 sprint, M= 1 sprint, L = 1.5 sprints, XL = 2 sprints, XXL = 3 sprints |  |  | Release Kernels
sprint | week | first day | Sprint goals voor kernels(prioritized every Friday) | teamfocus | Release D-Shell comp | Kernels | Events | Student testers
Sprint 1 | week 5 | 2017-01-30 | ?issuenr?: Delft3D Linux distribution | 0.5
| week 6 | 2017-02-06 | ?issuenr?: FM 2D-Morphology
Sprint 2 | week 7 | 2017-02-13 | ?issuenr?: FM 2D-Wave | 0.5
| week 8 | 2017-02-20 | ?issuenr?: DIMR: time issues |  | Patch release D-Hydro 1.2.4 / SOBEK 3.6.4 |  |  | x
Sprint 3 | week 9 | 2017-02-27 | ?issuenr?: RTC-Tools 1.x: no optimization | 0.7
| week 10 | 2017-03-06 | ?issuenr?: Testbenches (DIMR, FM)
Sprint 4 | week 11 | 2017-03-13 | ?issuenr?: merge D3D-WAVE with D-WAVE | 0.7
| week 12 | 2017-03-20 |  |  | Patch release D-Hydro 1.2.5 / SOBEK 3.6.5 | Scrum kick-off |  | x
Sprint 5 | week 13 | 2017-03-27 |  | 0.7
| week 14 | 2017-04-03 |  |  |  |  | FM Courses and D-Waq courses
Sprint 6 | week 15 | 2017-04-10 |  | 0.7
| week 16 | 2017-04-17 |  |  | Patch release D-Hydro 1.2.7 / SOBEK 3.6.7 |  |  | x
Sprint 7 | week 17 | 2017-04-24 |  | 0.6 |  | Feature freeze kernels
| week 18 | 2017-05-01 |  |  |  | Feature freeze DIMR
Sprint 8 | week 19 | 2017-05-08 |  | 0.6 |  | Delivery to Delta Shell
| week 20 | 2017-05-15 | [5 empty] | x
Sprint 9 | week 21 | 2017-05-22 |  | 0.8 | Do 25 mei: Rehearsal release D-Hydro 1.2.8 / SOBEK 3.6.8 | Feature freeze kernels |  | x
| week 22 | 2017-05-29 |  |  |  | Feature freeze DIMR
Sprint 10 | week 23 | 2017-06-05 |  | 0.8 |  | Delivery to Delta Shell
| week 24 | 2017-06-12 |  |  |  |  | DSD-NL | x
Sprint 11 | week 25 | 2017-06-19 |  | 1 | Do 22 juni: Release 2017.1 D-Hydro 1.2.9 / SOBEK 3.6.9 |  |  | x
| week 26 | 2017-06-26
Sprint 12 | week 27 | 2017-07-03 |  | 1
| week 28 | 2017-07-10 |  |  | Patch release NGHS D-Hydro 1.2.10 / SOBEK 3.6.10 |  |  | x
Sprint 13 | week 29 | 2017-07-17 |  | 1
| week 30 | 2017-07-24
Sprint 14 | week 31 | 2017-07-31 |  | 1
| week 32 | 2017-08-07 |  |  | Patch release D-Hydro 1.2.11 / SOBEK 3.6.11 |  |  | x
Sprint 15 | week 33 | 2017-08-14 |  | 1
| week 34 | 2017-08-21
Sprint 16 | week 35 | 2017-08-28 |  | 1
| week 36 | 2017-09-04 |  |  | Patch release D-Hydro 1.2.12 / SOBEK 3.6.12 |  |  | x
Sprint 17 | week 37 | 2017-09-11 |  | 1 |  | Feature freeze kernels
| week 38 | 2017-09-18 |  |  |  | Feature freeze DIMR
Sprint 18 | week 39 | 2017-09-25 |  | 1 |  | Delivery to Delta Shell
| week 40 | 2017-10-02 | [5 empty] | x
Sprint 19 | week 41 | 2017-10-09 |  | 1 | Do 12 okt: Rehearsal release D-Hydro 1.2.13 / SOBEK 3.6.13 | Feature freeze kernels |  | x
| week 42 | 2017-10-16 |  |  |  | Feature freeze DIMR
Sprint 20 | week 43 | 2017-10-23 |  | 0.8 |  | Delivery to Delta Shell | DSD-INT
| week 44 | 2017-10-30 |  |  |  |  | DSD-INT | x
Sprint 21 | week 45 | 2017-11-06 |  | 1 | Do 9 nov: Release 2017.2 D-Hydro 1.2.14 / SOBEK 3.6.14 |  |  | x
| week 46 | 2017-11-13
Sprint 22 | week 47 | 2017-11-20 |  | 1
| week 48 | 2017-11-27
Sprint 23 | week 49 | 2017-12-04 |  | 1 |  |  |  | x
| week 50 | 2017-12-11 |  |  | Patch release D-Hydro 1.2.15 / SOBEK 3.6.15
Niet opgenomen in de planning
KPP zesde-generatie modellen (medium/low)
Improve scripting (L)
3D visualisatie